## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US1 | An AI-powered fraud detection system for Aadhar leverages machine learning, OCR, and image classification techniques to verify document authenticity, detect anomalies, and ensure identity validation in real-time. | MUST HAVE | NO | MENTOR-521 | 3- Completed
S2 | S2 | US2 | The AI fraud detection system for Aadhar processes uploaded documents through classification, object detection, and OCR to extract and match key details, assess authenticity, and generate a validity score for each document. | SHOULD HAVE | NO | MENTOR-521 | 3- Completed
S3 | S3 | US3 | The AI fraud detection system for Aadhar automates document verification by classifying, detecting key elements, extracting text, and comparing data for authenticity. | MUST HAVE | NO | MENTOR-521 | 3- Completed
S4 | S4 | US4 | One must have knowledge of classification,OCR and detection models | SHOULD HAVE | research papers | MENTOR-521 | 3- Completed
S5 | S5 | US5 | classification model helps identify if the image is aadhar or non aadhar | MUST HAVE | YOLO | MENTOR-521 | 3- Completed
S6 | S6 | US6 | detection model helps detect the object | MUST HAVE | YOLO | MENTOR-521 | 3- Completed
S7 | S7 | US7 | OCR model helps extract the text | MUST HAVE | easyocr | MENTOR-521 | 3- Completed
S8 | S8 | US8 | backend is made through flask | MUST HAVE | flask | MENTOR-521 | 3- Completed
S9 | S9 | US9 | frontend is made with html,css and javascript | MUST HAVE | html,css,JS | MENTOR-521 | 3- Completed
S10 | S10 | US10 | frontend and backend are connected through ajax | MUST HAVE | AJAX | MENTOR-521 | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 7 | 6 | 7 | 8 | 7 | 7 | 7 | 12 | 4 | 8 | 4 | 8 | 8 | 7 | 7
SPRINT 1 BACKLOG
US001 | TID-01 | An AI-powered system to detect fraud | 2024-12-04 | 2024-12-06 | Anushka | Build | 3- Completed | 1 | 3 | 3 | 3 | 1 | 3 | 1 | 1 | 1 | 3 | 2 | 2 | 4 | 2 | 2
US001 | TID-02 | workfow consists of input,processing the images and table output | 2024-12-07 | 2024-12-10 | Anushka | Coding | 3- Completed | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 1 | 1 | 3 | 2 | 2 | 2
US001 | TID-03 | documents are discussed and analysed | 2024-12-11 | 2024-12-15 | Anushka | Coding | 3- Completed | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 1 | 1 | 1
US001 | TID-04 | use case research is done | 2024-12-16 | 2024-12-18 | Anushka | Coding | 3- Completed | 2 | 0 | 1 | 1 | 1 | 0 | 0 | 5 | 0 | 1 | 0 | 1 | 1 | 1 | 1
US001 | TID-05 | python practice kit completion | 2024-12-19 | 2024-12-20 | Anushka | Coding | 3- Completed | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | day 2 | lack of clarity | conducted meeting
Sprint 2 | day 4 | lack of clarity on workflow steps | group brainstorming
Sprint 2 | day 8 | template confusion | meeting with mentor
Sprint 3 | day 9 | not identifying use cases | conducted research
Sprint 3 | day 11 | difficulty in debugging | collaborated meeting
Sprint 4 | day13 | confusion about use cases | crearted priority matrix
Sprint 4 | day 15 | difficulty in database | meeting with mentor

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-04 | 2024-12-06 | Anushka | reviewing docs | making assumptions | participating | held discussion
2 | Sprint 2 | 2024-12-07 | 2024-12-10 | Anushka | prioritising | delaying | maintaining focus | acquiring knowledge
3 | Sprint 3 | 2024-12-11 | 2024-12-13 | Anushka | preparing | flusing through concept | asking for help | brainstorming
4 | Sprint 4 | 2024-12-14 | 2024-12-16 | Anushka | discussion | delaying discussion | collaborating | collaborated meeting